## How to use
TURN8 Go/No-Go Decision Template
A scorecard for corporate venture teams. Counts your results and suggests an outcome. The panel makes the decision.
Purpose | Record a gate review in one place: the criteria, the evidence, the decision and any conditions. Built for the gate at the end of Validation and Design, where the question is whether to spend real build money.
Step 1 | Open the Scorecard tab. Fill in the decision header (Part 1).
Step 2 | Agree the criteria and thresholds with the decision-makers at least two weeks before the review, and before the evidence is collected. The thresholds in the template are examples, not rules. Replace them with your own.
Step 3 | Mark each criterion that cannot be waived as must-meet (Yes in the Must-meet column).
Step 4 | At the review, set Met? to Yes or No for every criterion. Every criterion must be binary: met or not met.
Step 5 | Read the suggested outcome at the top of the Scorecard tab. Then record the decision in Part 4, with each condition, its owner and its deadline.
Decision rules | Go: every criterion is met. Conditional go: one or more criteria are not met, but each gap can be closed within a fixed period (for example 60 to 90 days) by a named owner. Stop: a gap cannot be closed in that window, or the evidence contradicts the thesis. There is no open-ended hold.
Must-meet criteria | If an unmet criterion is marked must-meet, the sheet does not suggest a plain conditional go. The panel has to agree a dated fix for that gap, or stop.
Colour legend | Light yellow cells with blue text are for you to edit. Everything else is calculated or fixed. Do not type over the cells in the Suggested outcome block.
Worked example | The Worked example tab shows a fictional logistics venture reaching its gate: ten of twelve criteria met, conditional go. It is illustrative and not a real client.
Important | This template supports a decision. It does not make it. Example thresholds are illustrative. It is general information and not financial, investment, legal or tax advice.
Source | TURN8 phase-gate method. Published with the article Go/No-Go Decision Template at turn8.co.

## Scorecard
Go/No-Go Scorecard
Part 1. Decision header
Field | Enter here | What to write
Venture name and phase |  | Name of the venture and the phase being closed (for example, Phase Two: Validation and Design)
Review date and facilitator |  | Date of the review and the person who runs the session
Decision-makers |  | Names and roles of the people who vote; the venture team does not vote
Strategic challenge |  | The corporate challenge this venture was started to solve, in one sentence
Capital released so far |  | Amount spent to date and amount requested for the next phase
Suggested outcome
Criteria listed | 12
Rated (Yes or No) | 0
Met | 0
Not met | 0
Not met and marked must-meet | 0
Can every gap be closed within the agreed window (for example 60 to 90 days)? |  | Answer only if some criteria are not met. Leave blank if all are met.
Suggested outcome | Rate every criterion (Yes or No) to see a suggestion.
The suggestion applies the TURN8 decision rules. The decision-makers decide, and the signed decision record in Part 4 is what closes the gate.
Part 2. Criteria scorecard
Dimension | Criterion (binary) | Evidence required | Must-meet? | Met? | Result or evidence reference
1. Customer evidence | At least 15 validated customer interviews across the target segments | Interview log with dates and segments
1. Customer evidence | Demand signal score above 60 (or your own agreed measure) | Demand dashboard export
1. Customer evidence | Written proof of willingness to pay from at least 3 potential buyers | Letters of intent, pilot orders or paid pilots
2. Problem-solution fit | Concept score at or above the agreed minimum | Concept test results
2. Problem-solution fit | Task completion rate in prototype testing at or above 80% | Prototype test report
3. Business model viability | LTV to CAC ratio of at least 3 | Unit economics model
3. Business model viability | CAC payback period no longer than 18 months | Unit economics model
3. Business model viability | Gross margin at or above the agreed floor | Cost and pricing model
4. Financial credibility | Bottom-up financial model with three scenarios | Model file reviewed by finance
4. Financial credibility | Capital requirement within the agreed ceiling | Funding request
5. Strategic alignment | Venture solves the strategic challenge set at the start | One-page strategic fit note
5. Strategic alignment | Venture fits the organisation's three-year strategy | Sign-off from the strategy lead
Example thresholds (the numbers in column C) are illustrative. Replace them with your own and agree them before the evidence is collected. Add your own criteria in the spare rows. Keep every criterion binary.
Part 3. Decision rules
Outcome | When to use it | What must be recorded
Go | Every criterion is met | Capital released, next-phase goals and owner
Conditional go | One or more criteria are not met, but each gap can be closed within a fixed period (for example 60 to 90 days) by a named owner | Each condition, owner, deadline and what happens if it is missed
Stop | A gap cannot be closed in that window, or the evidence contradicts the thesis | Reason for stopping, assets to reuse, team reassignment
This gate has no open-ended hold: a pause without a deadline usually becomes permanent drift. A conditional go gives the same breathing room with dates attached.
Part 4. Signed decision record
Outcome
Scorecard result (met of rated) | 0 of 0 criteria met
Condition (if any) | What must be done | Owner | Deadline |  | If missed
Decision-maker | Role | Signature | Date
Share the signed record with everyone involved within 48 hours of the review. A decision that is not written and shared can be reopened by whoever lobbies hardest.

## Worked example
Worked example: a logistics venture reaches its gate
Illustrative only, not a real client. A regional logistics group has spent a phase validating a freight-matching platform. The decision-makers agreed the criteria in advance. The team presents its evidence and the panel scores each line.
Criterion | Threshold | Result | Met? | Must-meet?
Validated interviews | 15 or more | 18 across 3 segments | Met | No
Demand signal score | Above 60 | 64 | Met | No
Written willingness to pay | 3 buyers | 2 buyers | Not met | No
Concept score | At least 7 of 10 | 7.6 | Met | No
Prototype task completion | 80% or more | 83% | Met | No
LTV to CAC | 3 or more | 3.4 | Met | No
CAC payback | 18 months or less | 14 months | Met | No
Gross margin | 35% or more | 31% | Not met | No
Bottom-up model, 3 scenarios | Required | Complete | Met | No
Capital requirement | SAR 12 million or less | SAR 10.5 million | Met | No
Solves the strategic challenge | Yes | Yes | Met | No
Fits the three-year strategy | Yes | Yes | Met | No
Criteria met | 10
Criteria not met | 2
Not met and must-meet | 0
Result | 10 of 12 criteria met
Decision
Conditional go. Two gaps remain and both can be closed. The record sets three conditions: secure a written commitment from a third buyer within 60 days, present a pricing or cost plan that reaches a 35% gross margin within 60 days, and release the capital in two tranches, with the second tranche released only when both conditions are met. If either condition is missed, the venture moves to a stop review.
In this example no criterion is marked must-meet. If gross margin had been marked must-meet, the Scorecard tab would ask the panel to agree a dated fix for it or stop.